## Worksheet
SN | Performance Tracking and Measuring Framework
Expected Output Deliverables and Performance Measurement
| Basic Information Entry | [5 empty] | 2024-Quarter-1 |  |  |  | 2024-Quarter-2 |  |  |  | 2024-Quarter-3 |  |  |  | 2024-Quarter-4
| Commitment | Output Deliverable | Output KPIs | Unit of Measurement | Baseline Value (Actual-2023) | 2024 Target | Delivery Milestone | Actual Delivery | Performance Measure | Performance Score (% of milestone) | Delivery Milestone | Actual Delivery | Performance Measure | Performance Score (% of milestone) | Delivery Milestone | Actual Delivery | Performance Measure | Performance Score (% of milestone) | Delivery Milestone | Actual Delivery | Performance Measure | Performance Score (% of milestone)
1 | Highway Expansion Project | Earthwork and Grading | Road Grading Speed | meters per day | 20 | 7 | 22 | 20 | 20 | 90.91 | 1232 | 1200 |  | 0 |  |  |  | 0 |  |  |  | 0 | Met target. | 0
|  |  | Average Daily Earthwork Progress | cubic meters per day | 5000 | 900 | 95 | 93 | 93 | 97.89 | 95 | 94 |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 807
|  | Asphalt Paving | Asphalt Thickness Compliance | percentage | 95 | 35 | 100 | 100 | 100 | 100 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0
|  | Traffic Sign Installation | Timely Traffic Sign Installation | percentage | 100 | 40 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 40
|  |  | Timely Traffic Sign Installation Training | percentage | 100 | 30 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 30
|  | Landscaping and Beautification | Landscaping speed | metres per day | 30 | 10 | 65 | 30 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 10
2 | Bridge Rehabilitation Initiative | Clearing
3 | Community Park Redevelopment
4 | Smart Street Lighting Project
5 | Dutse Housing Estate